## Sheet1
Team Skills Audit (Phoenix Mart)
Skill Level: 1 (No Knowledge) - 5 (Competent)
| Date Reviewed: 03/03/2022 |  | Completed By: Phoenix Mart Team | Version 1.0
NO# | Skill Required | Skill Level ( 1- 5) | Traning Action | Training Objective | Time (hrs) | Training Completion Deadline | Traning for?
1 | PHP Programming | 2.75 | Learn via different online resources available in the internet. | To become more efficient and implement it for the completion of back-end of the project. | 14.5 | 2022-03-19 | All Team Members
2 | HTML | 3.375 | Explore W3School and learn through execution. | To advance the skills required for creating a website, implementing all the functionalities provided by the language. | 10.75 | 2022-03-10 | Arju Adhikari, MD Aashif Ansari
3 | CSS | 3.375 | Watch recordings and lecture slides made available from level 3 and 4. | Using it to display the webpages using different styles and making it much more presentable. | 10.75 | 2022-03-12 | Arju Adhikari, MD Aashif Ansari
4 | Javascript | 2.25 | Explore different JavaTutorialPoint sites and excel the validation reqirements. | Learn functionalities necessary for advancing the basic and to define behaviour of webpage. | 13 | 2022-03-19 | All Team Members
5 | Moqup | 4 | Frequent use of the tools provided for creating wireframe. | To create a basic blueprint for the webpage. | 2
6 | QSEE | 4 | Going through notes from previous semester and exploring diagram tools more. | For designing diagram such as UML and ERD needed for developing ecommerce system. | 2.75
7 | Database Oracle | 3.13 | Watch YouTube videos related to subject matter and follow up resources. | For designing a efficient data storage and retrival system required for building a ecommerce website. | 13 | 2022-03-24 | All Team Members
8 | Photoshop | 3.5 | Follow up online resources such as videos and samples for designing. | To be efficient in the tools and to make its use. | 5 | 2022-03-06 | Nimisha Raut, Sajil Maharjan
9 | Illustrator | 3.25 | Grasp ideas and skills through tutors available online for free. | To create logo and vector graphics to use in the webpage. | 4.25 | 2022-03-06 | Nimisha Raut, Sajil Maharjan
10 | Milanote | 3 | Watch through tutorial video to learn the basic interface. | Make the optimum utilization of the facilities provided by the software. | 4 | 2022-03-07 | MD Aashif Ansari, Nimisha Raut, Sajil Maharjan
11 | Visual Studio Code | 3.25 | Look up for guidelines available on efficient use of the IDE. | For making maximum use of tools facilitated by the software while writing codes. | 2
12 | Awesome Font | 3.75 | Reviewing the website and practice to make use of the resources. | Include wide ranges of icons in the website to make it much more presentable. | 2.25 | 2022-03-06 | Nimisha Raut, Sajil Maharjan
13 | Github | 3 | Watch videos for guidance and use the interface more frequently. | For organized and managed sharing and storage of codes among the teammates. | 3 | 2022-03-16 | Arju Adhikari, Sajil Maharjhan
14 | Bootstrap | 2.88 | Surf online course and explore the bootstrap 5 website deeply. | For the framework's compatibility with all major browser versions and platforms, and has a superior grid system along with better styling in less time. | 5 | 2022-03-17 | Nimisha Raut, Sajil Maharjan
15 | Sandbox | 1.25 | Watch tutorial videos and take guidelines from the internet. | Make it use to create a PayPal interface and explore additional ways to use it. | 5.5 | 2022-03-29 | All Team Members
16 | XAMPP | 3.125 | Revise instructions provided previously by the tutor. | To local host and check the working of the webpage. | 2.75
17 | UI/UX Design | 3.125 | Practical approach to learn and advance the basics by analyzing and studying different resources available in the internet. | To develop an outline for the development of an ecommerce site. | 4.75 | 2022-03-08 | Nimisha Raut, Sajil Maharjhan
18 | Discord | 2.875 | Watch YouTube videos and follow along. | To communicate with team members and regular share of files. | 1.25 | 2022-03-05 | Arju Adhikari, Nimisha Raut
19 | MS Word | 4 | Search for guideline articles on internet when required. | Make it use throughout building of the project. | 1.5
20 | MS Excel | 2 | Surf the YouTube tutorials and learn the basic tools. | For effective and efficent store of the document related to the project. | 2.25 | 2022-03-06 | Arju Adhikari, MD Aashif Ansari
21 | MS Project | 1 | Learn from the very basic through self exploration as well as lecture guidance. | To manage and control the operation of tasks for directing a project. | 7.5 | 2022-03-28 | All Team Members
22 | PowerPoint | 3.375 | Follow guidelines and explore techniques to create a presentation. | To make presentation slides when required. | 1.75
23 | Adobe Premium Pro | 2 | Go through tutorial videos and be familiar with the software tools. | To edit videos and adjust the video sizes to place in the webpage. | 4.75 | 2022-03-16 | MD Aashif Ansari, Nimisha Raut, Sajil Maharjan